## Slide 1: Project Lantern: kickoff
Brightwater Studio, 3 March 2025. Presenter: Daniel Reyes

## Slide 2: Why we are doing this
Two clients, Harbour and Pine and Corvid Foods, have NDAs that forbid third parties from processing their work
Staff already try outside AI tools on their own
Goal: a private assistant that keeps client work inside the building

## Slide 3: What Lantern will do
Summarise meeting notes
Draft client emails
Search project documents
It will not decide anything about people

## Slide 4: Options we compared
A: cloud subscription, £22 per user per month, £3,168 a year for 12 people
B: hosted private instance, £780 per month, £9,360 a year
C: our own workstation, £17,258 in the first year
Recommended: C, because it is the only option that suits both NDAs

## Slide 5: Who does what
Maya Okafor: sponsor
Daniel Reyes: project owner
Priya Nair: builds and runs the workstation
Tomasz Lewandowski: policy and security
Hannah Frost: leads the pilot
Samir Haddad: budget

## Slide 6: Timeline
17 March: workstation ordered
21 March: AI use policy approved
27 March: hardware delivered; 28 to 31 March: set-up and first benchmark
7 April to 2 May: four-week pilot with four people
5 and 6 May: training for all staff
12 May: rollout to all 12 staff
21 September: first policy review

## Slide 7: Budget
One-off: £2,330 (workstation £2,150, UPS £180)
Every month: £1,244 (support retainer £1,200, electricity £35, backup storage £9)
First year in total: £17,258

## Slide 8: Risks and what we do about them
Someone pastes red data: policy and training before anyone gets an account
One machine can fail: nightly backup and a UPS battery unit
Too many people at once: three can chat together, a fourth waits
Knowledge sits with one person: Priya Nair writes down how to rebuild it